## Overview
RISK MANAGEMENT PLAN
Area:
Date:
Version:
|  | Purpose: | This tool is designed to identify, assess and evaluate the risks facing MLHU and provide a comprehensive report on a quarterly basis.
|  | Background: | This tool is designed to create a risk register that is consistent with the annual Standard Activity Report that is submitted annually to the Ministry.
Workbook Index
|  | Worksheet Name | Description
|  | Overview | This worksheet provides the overview of the project and a table of contents to navigate the workbook.
|  | Instructions | This worksheet provides users with the instructions for using this workbook. This tab should be reviewed prior to executing the risk assessment workbook. A process flowchart and detailed user guide are included.
|  | Risk Categories | This worksheet provides the definitions of the risk categories used to identify risks.
|  | Objectives | This worksheet highlights the risk management process.
|  | Risk Register | This worksheet is used to identify potential risk categories, assess risks and mitigation strategies, evaluate strenth of controls, monitor and report residual risks on a quarterly basis.
|  | Risk Matrix | This worksheet displays the results of the risk assessment into graphics for reporting and decision making purposes.
d |  | Risk Charts | This worksheet displays the results of the risk assessment into summary tables and charts.
|  | Risk Scales | This worksheet provides the ranking models used to conduct the risk assessment.
|  | Reference | This worksheet displays the drop down lists utilized in the risk register.

## Instructions
The MLHU Risk Management Process
Objectives
Identify
Evaluate
Assess
3.Open <Risk Register Tab> and input risk by entering ID # and Date Identified
Start
1.0 Consult the MLHU Risk Management Workbook
6.0 System automatically calculates "Risk Rating" as High, Medium, or Low
7.0 Enter Key Mitigation Strategies ("Controls")
8.0 Evaluate (Update) Current Strength of Controls
Consult <Risk Scales Tab>
2.0 Review the Risk Management Process <Objectives Tab>
5.0 Enter a description of the risk.
4.0 Select most appropriate Risk Category Consult <Risk Categories Tab>
End
Monitor & Report
5.0 Assess the impact and likelihood of each risk. Consult <Risk Scales Tab>
9.0 Determine level of residual risk for the current quarter based on the current strength of controls in place
Consult <Risk Scales Tab>
10.0 Enter (Update) the Most Responsible Leader to implement mitigation strategies for the current quarter

## Risk Categories
RISK CATEGORIES
Financial | Operational or Service Delivery | Strategic/Policy
Uncertainty around obtaining, committing, using, losing economic resources or not meeting overall financial budgets/commitments. | Uncertainty regarding activities performed in carrying out the entity's strategies or how the entity delivers services. | Uncertainty around strategies and policies achieving required results; or that old and/or new policies, directives, guidelines, legislation, processes, systems, and procedures fail to recognize and adapt to changes.
Stakeholder/Public Perception | People/Human Resources | Legal Compliance
Uncertainty around managing the expectations of the public, other governments, Ministries, or other stakeholders and the media to prevent disruption or criticism of the service and a negative public image. | Uncertainty as to the capacity of the entity to attract, develop and retain the talent needed to meet the objectives. | Uncertainty regarding compliance with laws, regulations, standards, policies, directives, contracts, MOU's and the risk of litigation.
Security | Information/Knowledge | Governance/Organizational
Uncertainty relating to breaches in physical or logical access to data and locations (offices, warehouses, labs, etc.) | Uncertainty regarding access to, or use of, inaccurate, incomplete, obsolete, irrelevant or untimely information, unreliable information systems; inaccurate or misleading reporting. | Uncertainty about maintenance or development of appropriate accountability and control mechanisms such as organizational structures and systems processes; systemic issues, culture and values, organizational capacity, commitment and learning and management systems, etc.
Political | Technology | Privacy
Uncertainty that events may arise from or impact the Minister's Office/Ministry, e.g. a change in government, political priorities, or policy direction. | Uncertainty regarding alignment of IT infrastructure with technology and business requirements; availability of technological resources. | Uncertainty with regards to exposure of personal information or data; fraud o identity theft; unauthorized data.
Environmental | Equity
Uncertainty usually due to the external risks facing an organization including air, water, earth, forests. An example of an environment, ecological risk would be the possible occurrence of a natural disaster and its impact on an organization's operations. | Uncertainty that policies, programs or services will have a disproportionate impact on the population.

## Risk Matrix
RISK MATRIX
Risk Priority Risk Map
Risk Matrix Interpretation
Risk maps provide an effective, means of identifying and prioritizing risks. Risks with a high Probability, and a medium to high Impact are the highest priority, however risk strategies should be developed to deal with all identified risks.
| Impact | 5 Threatens the success of the project
4 Substantial Impact on time, cost or quality
3 Notable impact on time, cost or quality
2 Minor impact on time, cost or quality
1 Negligible impact
|  | Ranking | 1 Unlikely to occur | 2 May occur occassionally | 3 Is as likely as not to occur | 4 Is likely to occur | 5 Is almost certain to occur
Likelihood
Legend
High Risk Priority
Medium Risk Priority
Low Risk Priority

## Risk Register
MLHU RISK REGISTER
IDENTIFY |  |  |  | ASSESS |  |  |  | EVALUATE |  | MONITOR & REPORT |  |  |  |  | Comments
ID | Date Identified | Risk Category | Risk Description | Impact (1-5) | Likelihood (1-5) | Risk Rating (H,M,L) | Key Mitigation Strategies ("Controls") | Actions Taken | Current Strength of Controls | Q1 Residual Risk | Q2 Residual Risk | Q3 Residual Risk | Q4 Residual Risk | Most Responsible Leader | Comments
1 | 2020-12-01 | Financial | The Health Unit has a balanced budget for 2024; however, there will be continued financial pressures as the Ministry's 1% increase is not enough to offset contractual obligations and other general inflation. | 4 | 5 | H | Increase Municipal contributions by 3% annually. Continue to lobby the Ministry for additional funding. Encourage the Ministry to provide reimbursement for COVID-19 administered vaccines. Possible re-structuring and direct impact to services delivered. | The City of London and County of Middlesex have been informed of the 3% increase to funding which was well received. COVID-19 funding has been approved by the Ministry, that coupled with restructuring has alleviated some pressure on 2024. The MOH and CEO have drafted a government relations strategy that includes advocacy for additional funding with each level of government (municipal/provincial/federal) across multiple ministries (Health, Children & Community Social Services, Finance, Immigration). Multi-year budget assumptions have been completed, and confirm that current funding levels do not keep pace with inflation. Options were being presented to the Board of Health at the June meeting. Both the MOH and CEO are actively participating in the funding reform discussions with the Ministry. Looking ahead to 2025 as a transition year as the new funding model (reform) is anticipated for 2026. Update: Exploring a one time extraordinary expenses submission to the Ministry for work related to COVID-19 and other disease outbreak work completed in 2024. | Ineffective | Moderate Risk | Significant Risk | Significant Risk |  | CEO
2 | 2022-03-23 | Technology | Cyber security threats remain a prominent risk to public agencies in the health sector. | 4 | 2 | M | Purchase of Cyber Insurance. Continued threat identification and mitigation through penetration testing and enhanced training for staff. | MLHU Cyber insurance has been renewed for 2024-25. Continued hardening of the MLHU environment, and ongoing training for staff. An enhanced training platform is being deployed. This includes the ability to quickly report Phishing or suspicious email for review, through Outlook. This technology provides safe notification of threats to IT optimizing response time and effectivness. Update: Investment in enhanced cyber training is showing positive results. Staff are identifying potential threats to the system, enabling IT to take corrective measures in a timely fashion. | Effective | Minor Risk | Minor Risk | Minor Risk
3 | June 30, 2022 | Political | The return of Public Health Modernization to the province's agenda as a result of the Provincial election and the uncertainty it will have on the structure and future of public health in Ontario. In August 2023 local Public Health agencies were encouraged to explore merger opportunities. Update: The window for submitting voluntary merger proposals to the province has now closed; additional clarity on the province's next steps may occur in the fall 2024. | 5 | 3 | H | MLHU will strive to mitigate this risk by preparing Board members to be engaged in conversation with provincial leadership, demonstrating high-quality integration and partnership with local and regional partners such as Ontario Health Team and Ontario Health West leadership, as well as developing a communication plan with staff that ensures that they are not distracted from their core public health work. MLHU is optimally positioned from a population/catchement perspective - we serve ~500,000 and growing. | Staff continue to engage with aLPHa and COMOH to seek clarity and endorse the role of a strengthened public health sector. The MOH and CEO continue to review local opportunities to show the importance of local public health work. MOH and CEO continue to engage partner agencies and Ministry to better understand associated threats/opportunities with respect to modernization/merger. Surrounding jurisdictions have shown no interest in merging with MLHU. Continue to monitor the external landscape for new developments. Update: Proposed changes currently sit with the Minister of Health and Premier's Office; however, uncertainty around mergers and funding formula remain in the context of an expected upcoming provincial election. | Not able to rate | Moderate Risk | Moderate Risk | Moderate Risk |  | CEO MOH
4 | 2022-09-30 | Legal/Compliance | Class Action Suit against long term care homes (LTCH) leads to a claim brought against MLHU in regards to direction provided to the long term care homes during the COVID-19 pandemic response. | 4 | 2 | M | Enter into a tolling agreement with the LTCH to minimize the legal costs of being named in the claim before the risk of liability is determined. | Signed tolling agreement after consultation with legal counsel. Tolling agreement has been extended 12 months (expires Oct. 2024). Class Action suit was certified in January 2024. PRCR Manager to reassess risk September 2024 to determine if tolling agreement will be further extended. Update: MLHU received an updated tolling agreement in October 1, 2024 for review. Vetting with legal prior to extending tolling agreement. Current agreement is valid until October 30, 2024. Intent is to extend the tolling agreement prior to October 30, 2024. | Effective | Minor Risk | Minor Risk | Minor Risk |  | CEO
5 | 2023-01-19 | Technology | MLHU uses RSA tokens to provide VPN access to various databases and web applications. With decentralized management of RSA tokens, there is potential for management issues including token assignment changes and collection. | 3 | 3 | M | Token management is to be centralized by the MLHU IT team with policies and processes in place to ensure that tokens and associated software access it tracked throughout onboarding, staff role changes, and termination. | Risk has been reduced through enhanced internal asset management practices. IT team received additional training in support of lead role for future token management. IT team has completed training and is assuming the lead role for this work. Update: Transition to IT will continue into Q4, with full transition starting in September 2024. Anticipate transition will be complete in November 2024. | Partly Effective | Moderate Risk | Moderate Risk | Moderate Risk |  | CEO
6 | 2024-01-03 | People/Human Resources | As a result of the restructuring, the layoff process in the ONA Collective Agreement allows for bumping onto any team where a nurse has higher seniority. This resulted in 20 PHNs moving into new teams where most of them had no experience as of Jan. 2, 2024. The creation of 3 new teams merged from previous teams also created uncertainty and inexperience requiring training and skill development for the new work of these teams. The first quarter of 2024 had reduced productivity as teams were in a forming stage, new members are in training, and experienced members are mentoring. In addition to decreased productivity, staff morale was decreased due to the loss of work, colleagues and movement onto teams that were not preferred. Update: Certain teams and leaders continue to demonstrate decreased resilience, secondary to restructuring/post-pandemic/etc. | 4 | 5 | H | Leaders put orientation plans in place for new members joining their teams and adjusted the workload and productivity expectations while new staff were in training. New team members all started with their teams on the same date so that orientations would be aligned and could be done in groups. The first two weeks of January were dedicated to team building discussions for the newly merged teams. Two change management virtual workshops for all staff and one for leaders specifically were held in December and January around building resilience, setting boundaries, self care, and creating psychological safety, led by our wellness providers to help staff with coping through the changes. Update: Priority setting exercise to mitigate / load level workload pressures. | An external consultant was hired to facilitate solution-focused dialogue among the 3 newly merged teams to support change management through acknowledging the loss of the work and team members, as well as the learning how to function in the "neutral zone", a place of uncertainty. Following the success of these sessions, the consultant attended an MLHU Leadership Team meeting to share the communication model with all leaders for implementation within their teams. To mitigate leader workload issues some agency wide initiatives/projects are being deferred or load leveled across multiple employees to reduce individual burden. Additionally, the health unit has invested in Associate Managers for larger teams with heavier workloads due to clinical or time sensitive nature of the work. The increased leadership model has been impacted by leaves and retirement, so the leadership has not been at full compliment. Update: Current Associate Manager compliment is fully staffed. Home positions are strategically gapped, creating workload challenges on teams with enhanced workloads - IDC, VPD. The agency conducted a priority setting exercise, shifting some priorities to mitigate workload pressures. | Partly Effective | Significant Risk | Significant Risk | Significant Risk |  | CEO MOH
Note on D7: Risk Category: Once you have identified your risks you can group them into categories to help with managing them. An example would be Technology, Resource, training, etc.
Note on E7: Risk Description: Identify anything that might have a negative impact on the project. Your description should outline the risk to the project.
Note on F7: Probability: Probability of the risk materializing. Refer to worksheet <Reference> for additional guidance. 1 - Very unlikely to occur (Remote) 2 - Unlikely to occur (Unlikely) 3 - Even chance of occurring or occasional (Possible) 4 - Likely to occur (Likely) 5 - Very likely to occur (Expected)
Note on G7: Impact: Impact to the department/ project if the risk materializes. Refer to worksheet <Reference> for additional guidance. 1 - Negligible 2 - Minor 3 - Moderate 4 - Serious 5 - Critical
Note on H7: Risk Priority: H = 5 Prob/5 Impact H = 5 Prob/4 Impact H = 5 Prob/3 Impact H = 4 Prob/5 Impact H = 4 Prob/4 Impact H = 4 Prob/3 Impact H = 3 Prob/5 Impact M = 5 Prob/2 Impact M = 4 Prob/2 Impact M = 3 Prob/3 Impact M = 3 Prob/4 Impact M = 2 Prob/3 Impact M = 2 Prob/4 Impact M = 2 Prob/5 Impact M = 1 Prob/5 Impact L = 5 Prob/1 Impact L = 4 Prob/1 impact L = 3 Prob/1 Impact L = 2 Prob/1 Impact L = 1 Prob/1 impact L = 3 Prob/2 Impact L = 2 Prob/2 Impact L = 1 Prob/2 impact L = 1 Prob/3 Impact L = 1 Prob/4 Impact Refer to worksheet <Risk Maps> which shows these ratings in a chart Note 1) This column is automatically populated based on the probability and impact rating
Note on P7: Most Responsible Person (MRP): The MRP is the person who is responsible for working with the subject matter experts to identify the Risk Control plan and then overseeing the execution and tracking of the control of the risk.
Note on Q7: Comments: Insert any comments that are relevant to the risk

## Risk Charts
RISK CHARTS
Summary Tables and Charts:
|  | Risk Response Tactic |  | Total
|  | Risk Priority |  | Count | Percent
|  | High |  | 3 | 50%
|  | Medium |  | 3 | 50%
|  | Low |  | 0 | 0%
|  | Total |  | 6 | 100%
Note that the charts are based on the subtotals and exclude risks that were "Not Assessed (NA)", except Risk Priority
Other Summary Information:
|  | Probability Summary |  | Total |  | Impact Summary |  | Total
|  | Score | Rank | Count | Percent | Score | Rank | Count | Percent
|  | 1 | Very unlikely to occur (Remote) | 0 | 0% | 1 | 1) Negligible | 0 | 0%
|  | 2 | Unlikely to occur (Unlikely) | 0 | 0% | 2 | 2) Minor | 2 | 33.33%
|  | 3 | Even change of occurring (Possible) | 1 | 16.67% | 3 | 3) Moderate | 2 | 33.33%
|  | 4 | Likely to occur (Likely) | 4 | 66.67% | 4 | 4) Serious | 0 | 0%
|  | 5 | Very likely to occur (Expected) | 1 | 16.67% | 5 | 5) Critical | 2 | 33.33%
|  | Total |  | 6 | 100% | Total |  | 6 | 100%
Status Updates
|  | Residual Risk Trending |  | Total
|  | Score | Rank | Count | Percent
|  | Dec | Decrease | #REF! | #REF!
|  | NC | No Change | #REF! | #REF!
|  | Inc | Increase | #REF! | #REF!
|  | Subtotal |  | #REF! | #REF!
|  | Not Assessed (NA) |  | #REF! | #REF!
|  | Total |  | #REF!
Note that the chart is based on the subtotal and exclude risks that were "Not Assessed (NA)"
Note on S8: Subtotal: Excludes risks that are not assessed (such as low risks if the team decided to only assess high and medium priority risks)
Note on D99: Subtotal: Excludes risks that are not assessed (such as low risks if the team decided to only assess high and medium priority risks or risks that have an "Accept" Risk Response Tactic)

## Risk Scales
RISK SCALES
Risk Rating Scale:
VALUE | LIKELIHOOD | IMPACT | SCALE
1 | Unlikely to occur | Negligible Impact | Very Low
2 | May occur occasionally | Minor impact on time, cost or quality | Low
3 | Is as likely as not to occur | Notable impact on time, cost or quality | Medium
4 | Is likely to occur | Substantial impact on time, cost or quality | High
5 | Is almost certain to occur | Threatens the success of the project | Very High
Current Strength of Controls Scale:
SCORE | RANK | PRESENSE OF CONTROL | EFFECTIVENESS | RESIDUAL RISK
0 | Not able to rate | There are no controls in place to assign a rating |  | Significant
1 | Very ineffective (Virtually no controls) | Very few, if any, controls are in place | Controls are ineffective at mitigating the risk | Significant
2 | Ineffective (Low control effectiveness) | Limited controls are in place | Only a limited number of the controls are effective | Moderate
3 | Partly effective (Moderate control effectiveness) | A moderate number of controls are in place | The controls are adequate at mitigating part of the risk | Moderate
4 | Effective (High control effectiveness) | The majority of controls are in place | The controls mitigate the majority of the risk | Minor
5 | Very effective (Very high control effectiveness) | Nearly all of the required controls are in place | The controls are effective at mitigating the risk | Minor
Residual Risk:
RESIDUAL RISK | DESCRIPTION
Significant | Represents the highest residual risk exposure as the assessed level of risk control effectiveness is insufficient for the level of risk. Management should consider improving risk control plans for these risks.
Moderate | Represents additional residual risk exposure that could be investigated further as the assessed risk control effectiveness is not propitiate with the level of risk. Control plans should be documented and reviewed or appropriateness.
Minor | Areas where the risk control effectiveness is proportionate with the level of risk.

## Reference
Strength of Controls | Residual Risk | Risk Categories
Not able to rate | Significant Risk | Environment
Very Ineffective | Moderate Risk | Equity
Ineffective | Minor Risk | Financial
Partly Effective |  | Governance/Organizational
Effective |  | Information/Knowledge
Very Effective |  | Legal/Compliance
Operational/Service Delivery
People/Human Resources
Political
Privacy
Security
Stakeholder/Public Perception
Strategic/Policy
Technology